JBB Portal — Forecasting, Cashflow & Profit Reporting

Proposed scope for review · Draft v0.1 · 20 July 2026 · Prepared by Nigel Reilly / Jewel Group

# 1. Purpose

This document turns your recent messages (the Excel mock-up, the eque2 reference, and the notes on profit and the FD dashboard) into a concrete proposal we can agree before anything is built. Each section describes what we understand you want, how it would work against the portal’s live figures, and the questions we need answered to build it right first time. Nothing here is built yet — please mark up anything that reads wrong.

# 2. Definitions already in place

These are live on the Financials tab today and every feature below reuses them — one set of numbers throughout:

- Contract Sales Value — the valuation report’s counting lines (contract works, provisional sums, contingency, variations).

- Target Cost Value — Contract Sales Value with the standard margin backed out; what the line should cost.

- Work Orders — value committed to work orders (order book, not yet necessarily billed).

- Non-WO Cost of Sales — actual allocated spend not linked to any work order (including approved labour).

- Forecasted Cost of Sales — Work Orders + Non-WO Cost of Sales; the expected total cost of the line.

- Drawdown — Target Cost Value − Forecasted Cost of Sales; funds still available (negative = overspent).

- Actual Cost of Sales — reference column: allocated Xero purchase spend, used for allocating invoices to work orders.

# 3. Workstream A — Phased forecast grid (cashflow)

A new Cashflow forecast table, matching the shape of your Excel: one row per revenue line and per cost line (by cost code), columns for each month, with the phased amounts entered against them. Worked from your example:

|  | Balance | Aug | Sep | Oct | Nov | Dec | Total | Variance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Revenue — cost code | £100,000 | £20,000 | £20,000 | £20,000 | £20,000 | £20,000 | £100,000 | £0 |
| Cost — cost code | (£80,000) |  | (£40,000) |  | (£40,000) |  | (£80,000) | £0 |

How it stays honest:

- The Balance column is pulled live from the portal — never typed. Revenue rows draw from the valuation (contract value less certified to date); cost rows draw from the drawdown remaining per cost code.

- The month cells are the forecast — phased by you (or pre-spread automatically, then adjusted).

- Total sums the phased months per row; Variance = Balance − Total. A non-zero variance means the phasing no longer explains the live balance — flagged in red, never hidden.

- A net movement line and a cumulative cash position line run along the bottom, so any month the project goes cash-negative is visible at a glance.

- Export to Excel in exactly this layout.

Questions for you

- Columns: calendar months, or valuation cycles? (If valuations are monthly these coincide — confirm the anchor date.)

- Cash timing: should revenue land in the month the valuation is certified, or offset by the client’s payment terms (how many days)? Same question for supplier payments (e.g. 30 days end-of-month?).

- When a work order has no phasing entered, how should we pre-spread it — evenly to its expected completion, or leave blank until phased by hand?

- Horizon: how many months forward should the grid run (fixed 12, or to project end)?

# 4. Workstream B — Forecast tab, change tracking & approval

Your note: “Extra TAB – forecast – Track when changed and reasoning means I can manage this correctly” and “Approval to change number based on forecast – Work on Budgeted / vs targets.” Proposed:

- Every change to a forecast cell records who, when, old → new value, and a required reason — a visible history against each row.

- A month-end snapshot of the whole forecast, so “what we said in July” is preserved and this month’s movement can be reported against it.

- Changes to budgeted figures (targets) — as opposed to phasing — require an approval step before they take effect.

Questions for you

- Who approves budget changes — you, James, either, or role-based?

- Does re-phasing within the same total need approval, or only changes that move a row’s total / a budget figure?

- Snapshot cadence — month-end automatic, on-demand, or both?

# 5. Workstream C — Profit: three measures, always £

Per your notes, profit is reported three ways, side by side, always as monetary values:

| Measure | Calculation | Answers |
| --- | --- | --- |
| Current profit | Claimed to date − costs to date | Where are we right now? |
| Forecast profit | Contract Sales Value − Forecasted Cost of Sales | Where will we land? |
| Budget profit | Contract Sales Value − Target Cost Value (the standard margin) | Where should we land? |

On “Moving Drawdown to £0 available and then Profit is the above”: we read this as — as forecasting matures, every line’s target is either committed, phased or released, drawdown trends to £0, and the headline number becomes Forecast profit rather than a remainder realised only when a line is locked. The lock would still exist (to freeze a finished line and bank its result), but profit reporting would no longer wait for it.

Questions for you

- “Current costs” in Current profit — Actual Cost of Sales (invoiced spend), or Forecasted Cost of Sales to date? We propose Actual.

- Do you agree the lock stays as a freeze mechanism, with profit reported continuously from the three measures above?

- Budget profit — confirm the standard margin the portal should carry (you mentioned 10%).

# 6. Workstream D — FD dashboard

A finance view keeping the first five columns of the financial summary (Code, Cost Centre, Contract Sales Value, % Complete, Claim Value), followed by the forecast columns and the three profit measures — all in £.

Questions for you

- Is this per project, across all live projects, or both (a group roll-up that drills into each project)?

- Who sees it — finance only, or directors too?

# 7. Workstream E — Raising WOs for materials against drawdown

Your note “Raise drawdown WO’s for materials”: we read this as bringing materials purchasing into the work-order pipeline — raising orders against a line’s remaining drawdown — so spend that today lands as Non-WO becomes committed up front and the forecast tightens. This is a meaningful procurement feature and we suggest scoping it separately once A–D are agreed.

Questions for you

- Confirm the intent: materials ordered through WOs against drawdown, reducing the Non-WO bucket over time?

# 8. Suggested order of delivery

- First — Workstream C (profit measures) and D (FD dashboard): fastest to deliver, all inputs already exist.

- Second — Workstream A (phased forecast grid + Excel export).

- Third — Workstream B (change tracking, snapshots, approvals) — designed alongside A so history is captured from day one.

- Then — Workstream E (materials WOs), scoped on its own.

Please mark up this document or reply against the question numbers — once agreed, we’ll build to it.